## Sheet1
PE-CE OUTSOURCED REPORT
AS OF: May 16 2024
FOR REGION(S): Region 1
FOR ADMIN ID(S): ODOT, ODOT/LOCAL
Report Contact:PMO
FOR COUNTY(S): ALL
FOR KEY NUMBER(S): ALL
FOR DBE GOAL: All
STIP-FP Data |  | MSP Data | [6 empty] | Programmed STIP-FP Data | [5 empty] | Calculation | MSP Data |  | CRCT
Key # |  | Project Name |  |  | PCS Region | ODOT Lead | Outsourced PE | Outsourced CE | Project Description | Admin By | County | Work Type | PE/PL Programmed Budget | Total Programmed Project Budget | Anticipated RFP Release Time | Kick-off Meeting Date | Bid Let Date | Anticipated DBE Goal
22504 |  | I-84: Corbett Interchange - Multnomah Falls Phase 2 |  |  | Region 1 | UMANA LUIS | Yes | Yes | Rehabilitation and replacement of culverts to repair damage and prevent road deterioration. | ODOT | MULTNOMAH | CULVRT | 1186422 | 3546648 | 4th QTR, 2023 | 2024-05-08 17:00 | 2025-05-12 17:00 | TBD
22603 |  | I-405 Fremont bridge (Willamette River) East & West ramps |  |  | Region 1 | DEVASSIE ROBERT J | Yes | Yes | Inspect the paint condition on all approach ramps, develop a schedule of painting phases, repaint the highest priority ramps. | ODOT | MULTNOMAH | BRIDGE | 11632000 | 11759000 | 1st QTR, 2024 | 2024-05-29 17:00 | 2026-01-22 17:00 | TBD
22621 |  | US30 curb ramps (Hood River) |  |  | Region 1 | MILLER JAMIE N. | No | Yes |  | ODOT |  |  |  |  | 1st QTR, 2024 | 2022-07-27 08:00 | 2024-09-26 17:00 | TBD
Report Total: 3

## Sheet2
About this report Report name: PE-CE Outsourced Report Purpose: To provide forecasted outsourced work to industry partners. This report is posted to the external ODOT Procurement website weekly. Definitions and filters: Filter(s): Projects show on this report according to the following: PE & CE or just PE outsourced: Project will be on the report for 12 months before the PDT kick off date until 3 months after the PDT kick off date. Just CE outsourced: Project will be on the report for 9 months before the bid let date until 1 month after the bid let date. Anticipated RFP Release Time calculation: PE & CE or just PE Outsourced: PDT Kick off - 140 days Just CE outsourced: PS&E Submittal date - 180 days Data sources: RMS, STIP, CivilRights