## Sheet1
PE-CE OUTSOURCED REPORT
AS OF: May 16 2024
FOR REGION(S): Region 2
FOR ADMIN ID(S): ODOT, ODOT/LOCAL
Report Contact:PMO
FOR COUNTY(S): ALL
FOR KEY NUMBER(S): ALL
FOR DBE GOAL: All
STIP-FP Data |  | MSP Data | [6 empty] | Programmed STIP-FP Data | [5 empty] | Calculation | MSP Data |  | CRCT
Key # |  | Project Name |  |  | PCS Region | ODOT Lead | Outsourced PE | Outsourced CE | Project Description | Admin By | County | Work Type | PE/PL Programmed Budget | Total Programmed Project Budget | Anticipated RFP Release Time | Kick-off Meeting Date | Bid Let Date | Anticipated DBE Goal
22627 |  | OR132: Green Acres Rd to Goodpasture Island Rd |  |  | Region 2 | CARY MOLLY | Yes | No |  | ODOT |  |  |  |  | 1st QTR, 2024 | 2024-06-13 17:00 | 2026-03-16 17:00 | TBD
22656 |  | Luckiamute River, Helmick Road bridge (Polk Co) |  |  | Region 2 | GREENWAY VALERIE | Yes | Yes | Rehabilitation of bridge including seismic retrofit, erosion control repair and other general maintenance needs to preserve the historic integrity of the bridge. | ODOT/LOCAL | POLK | BRIDGE | 698300 | 3828500 | 2nd QTR, 2024 | 2024-10-21 17:00 | 2026-07-29 17:00 | TBD
22657 |  | Dougherty Slough, Blum Lane, Prince bridge (Tillamook Co) |  |  | Region 2 | NEAL NATHAN E | Yes | Yes | Replace the bridge in order to meet current bridge standards. | ODOT/LOCAL | TILLAMOOK | BRIDGE | 655400 | 3753700 | 2nd QTR, 2024 | 2024-11-06 17:00 | 2026-05-19 17:00 | TBD
22658 |  | Ash Swale, Patty Lane bridge (Yamhill Co) |  |  | Region 2 | GREENWAY VALERIE | Yes | Yes | Replace the bridge in order to meet current road standards. | ODOT/LOCAL | YAMHILL | BRIDGE | 915100 | 5198400 | 2nd QTR, 2024 | 2024-08-19 17:00 | 2026-04-20 17:00 | TBD
22660 |  | Small (Mt. View) Creek/Elliot Circle bridge (Benton Co) |  |  | Region 2 | DUNAWAY TYLER | Yes | Yes | Replace the bridge in order to meet current road standards. | ODOT/LOCAL | BENTON | BRIDGE | 434900 | 2225300 | 1st QTR, 2024 | 2024-05-30 17:00 | 2026-03-09 17:00 | TBD
22699 |  | Bellfountain Rd: Chapel Dr. to Alpine Rd. (Benton County) |  |  | Region 2 | DUNAWAY TYLER | Yes | Yes | Make improvements from Chapel Dr. to Alpine Rd. on Bellfountain Rd to reduce the number and severity of collisions. Improvements include: installing centerline rumble strips from MP 1.4 to MP 12.9, and from MP 14.9 to MP 15.7. Add intersection warning aids at Chapel Drive, 53rd Street, Airport Road, Llewellyn Road, Decker Road, Greenberry Road, Dawson Road, and Alpine Road. Intersection warning aids may include new street signs, larger stop signs, reflectorized sign posts, rumble strips across the lanes on Llewellyn Road, reflectorized backplates on overhead flashing beacons, post mounted flashing beacons, and installing red diamond signs at T-intersections. | ODOT | BENTON | SAFETY | 176529 | 780698 | 4th QTR, 2024 | 2025-03-17 17:00 | 2027-09-07 17:00 | TBD
22726 |  | NW Oregon lighting & enhanced intersection warning (2027) |  |  | Region 2 | NESS BILL | Yes | Yes | Complete design to install signs, striping other devices at various locations throughout Region 2 to reduce traffic incidents and increase safety. | ODOT | CLATSOP | SAFETY | 480382 | 495110 | 1st QTR, 2024 | 2024-07-16 17:00 | 2026-08-27 17:00 | TBD
22786 |  | OR18: Long Fiber Road - Murphy Hill |  |  | Region 2 | NESS BILL | Yes | Yes | Complete design to repave the road to repair deterioration, improve smoothness and reduce maintenance costs. | ODOT | POLK | PRESRV | 1095571 | 1095571 | 1st QTR, 2024 | 2024-06-07 17:00 | 2026-09-24 17:00 | TBD
22787 |  | OR6: MP 4.4-9.0 |  |  | Region 2 | MUHLY Anita | Yes | Yes | Complete design to repave the road to repair deterioration, improve smoothness and reduce maintenance costs. | ODOT | TILLAMOOK | PRESRV | 868791 | 868791 | 1st QTR, 2024 | 2024-06-20 17:00 | 2025-11-20 17:00 | TBD
22792 |  | OR18: S McMinnville Interchange - E McMinnville Interchange |  |  | Region 2 | WELCH PAUL | Yes | Yes | Complete design to repave the road to repair deterioration, improve smoothness and reduce maintenance costs. | ODOT | YAMHILL | PRESRV | 1604791 | 1825718 | 4th QTR, 2023 | 2024-05-02 17:00 | 2026-11-05 17:00 | TBD
22794 |  | US101: MP 23.9 culvert replacement |  |  | Region 2 | MUHLY Anita | Yes | Yes | Design and right of way/utility activities to replace the culvert at mile point 23.9 for driver safety. | ODOT | CLATSOP | CULVRT | 293255 | 355568 | 1st QTR, 2024 | 2024-06-17 17:00 | 2027-01-21 17:00 | TBD
22797 |  | OR47: MP 83.6 Illumination Replacement (Banks) |  |  | Region 2 | MUHLY Anita | Yes | Yes | Complete design to replace the lights and poles at this location to provide better illumination. | ODOT | WASHINGTON | OP-SSI | 374107 | 374107 | 3rd QTR, 2024 | 2025-01-13 17:00 | 2027-03-26 17:00 | TBD
22902 |  | US101 at Broadway Street Signal Upgrades (Seaside) |  |  | Region 2 | MUHLY Anita | Yes | Yes | Complete design to install turn lanes, rebuild/replace signals and update curb ramps to increase safety and traffic flow at this intersection. | ODOT | CLATSOP | SAFETY | 871844 | 1882139 | 2nd QTR, 2024 | 2024-08-30 17:00 | 2027-08-19 17:00 | TBD
23118 |  | US101: New Youngs Bay bridge |  |  | Region 2 | MUHLY Anita | Yes | Yes | Complete design to apply overlay to deck and replace the rails to increase the bridge life and safety. | ODOT | CLATSOP | BRIDGE | 1624159 | 1624159 | 4th QTR, 2024 | 2025-03-05 17:00 | 2027-08-17 17:00 | TBD
23122 |  | OR99E: Willamette R (Harrisburg) bridge |  |  | Region 2 | STOUDER CHARLES | Yes | No | Complete design to update the bridge rails to meet current safety standards and accommodate the high volume of truck traffic. | ODOT | LANE | BRIDGE | 994921 | 1187524 | 2nd QTR, 2024 | 2024-10-29 17:00 | 2027-10-18 17:00 | TBD
23127 |  | US101: Siuslaw River Bridge (Florence) |  |  | Region 2 | NEAL NATHAN E | Yes | Yes | Complete design to install overlay, concrete repair to the deteriorating columns, remove and replace/retrofit deck joints, and construct erosion control measures to help preserve the bridge. | ODOT | LANE | BRIDGE | 574330 | 574330 | 4th QTR, 2024 | 2025-03-04 17:00 | 2027-03-18 17:00 | TBD
23141 |  | Sand Creek, Sand Lake Road "Atkinson" bridge (Tillamook Co) |  |  | Region 2 | NEAL NATHAN E | Yes | Yes | Replace the bridge with a new one to meet current bridge standards. | ODOT/LOCAL | TILLAMOOK | BRIDGE | 665100 | 3465500 | 2nd QTR, 2024 | 2024-11-06 17:00 | 2026-05-19 17:00 | TBD
23142 |  | Old Railroad Grade (N Yamhill River) bridge |  |  | Region 2 | GREENWAY VALERIE | Yes | Yes | Replace the bridge to meet current standards. | ODOT/LOCAL | YAMHILL | BRIDGE | 1244000 | 6975400 | 2nd QTR, 2024 | 2024-09-23 17:00 | 2026-05-12 17:00 | TBD
23503 |  | Mill Creek Greenway Trail System (Woodburn) |  |  | Region 2 | ARANA DAVID | Yes | Yes | Add 1.3 miles of five new trails to connect existing Mill Creek trail system 1) Evergreen (s. of W. Hays St.) to approximately Ben Brown Lane; 2) Wyffels Park; 3) Woodburn High School; 4) Settlemier Park; 5) Hermanson Pond Trail Extension. The paths will improve access and safety for people walking and biking. | ODOT/LOCAL | MARION | BIKPED | 390059.07 | 1932369.33 | 2nd QTR, 2024 | 2024-09-05 17:00 | 2027-08-23 17:00 | TBD
Report Total: 19

## Sheet2
About this report Report name: PE-CE Outsourced Report Purpose: To provide forecasted outsourced work to industry partners. This report is posted to the external ODOT Procurement website weekly. Definitions and filters: Filter(s): Projects show on this report according to the following: PE & CE or just PE outsourced: Project will be on the report for 12 months before the PDT kick off date until 3 months after the PDT kick off date. Just CE outsourced: Project will be on the report for 9 months before the bid let date until 1 month after the bid let date. Anticipated RFP Release Time calculation: PE & CE or just PE Outsourced: PDT Kick off - 140 days Just CE outsourced: PS&E Submittal date - 180 days Data sources: RMS, STIP, CivilRights