## Sheet1
PE-CE OUTSOURCED REPORT
AS OF: May 15 2024
FOR REGION(S): Region 4
FOR ADMIN ID(S): ODOT, ODOT/LOCAL
Report Contact:PMO
FOR COUNTY(S): ALL
FOR KEY NUMBER(S): ALL
FOR DBE GOAL: All
STIP-FP Data |  | MSP Data | [6 empty] | Programmed STIP-FP Data | [5 empty] | Calculation | MSP Data |  | CRCT
Key # |  | Project Name |  |  | PCS Region | ODOT Lead | Outsourced PE | Outsourced CE | Project Description | Admin By | County | Work Type | PE/PL Programmed Budget | Total Programmed Project Budget | Anticipated RFP Release Time | Kick-off Meeting Date | Bid Let Date | Anticipated DBE Goal
20378 |  | Archie Briggs Rd (Deschutes River) Bridges |  |  | Region 4 | STEWART SCOTT G | Yes | Yes | Replace bridges 17C05 & 17C040 with ones that meet current standards. | ODOT/LOCAL | DESCHUTES | BRIDGE | 1160283 | 6222483 | 4th QTR, 2023 | 2024-02-20 17:00 | 2026-12-17 17:00 | TBD
22042 |  | 6th St. Viaduct: Bridge over Spring St. and Union Pacific RR |  |  | Region 4 | STEWART SCOTT G | Yes | Yes | Rehabilitate bridge components to improve the structural condition of the structure. | ODOT/LOCAL | KLAMATH | BRIDGE | 1187600 | 6076900 | 1st QTR, 2024 | 2024-06-17 17:00 | 2027-06-11 17:00 | TBD
23199 |  |  |  |  | Region 4 | STEWART SCOTT G | Yes | Yes | Rehabilitate bridge to remove load rating and update other structural items to improve integrity of the bridge | ODOT/LOCAL | JEFFERSON | BRIDGE | 670000 | 4724100 | 2nd QTR, 2024 | 2024-08-26 17:00 | 2025-12-18 17:00 | TBD
23494 |  | Hawthorne Ave Pedestrian & Bicyclist Overcrossing (Bend) |  |  | Region 4 | CHARLTON CARI | Yes | No | Provide safe access for pedestrians and bicyclists by designing and constructing a bridge over US97 and BNSF railroad connecting east Hawthorne Avenue to downtown Bend. | ODOT/LOCAL | DESCHUTES | BIKPED | 5072229.21 | 25825661 | 1st QTR, 2024 | 2024-08-14 17:00 | 2026-09-03 17:00 | TBD
Report Total: 4

## Sheet2
About this report Report name: PE-CE Outsourced Report Purpose: To provide forecasted outsourced work to industry partners. This report is posted to the external ODOT Procurement website weekly. Definitions and filters: Filter(s): Projects show on this report according to the following: PE & CE or just PE outsourced: Project will be on the report for 12 months before the PDT kick off date until 3 months after the PDT kick off date. Just CE outsourced: Project will be on the report for 9 months before the bid let date until 1 month after the bid let date. Anticipated RFP Release Time calculation: PE & CE or just PE Outsourced: PDT Kick off - 140 days Just CE outsourced: PS&E Submittal date - 180 days Data sources: RMS, STIP, CivilRights