## Totals
WORKLOAD SUMMARY
Focus Areas* | Staff Work Days Allocated | [9 empty] | Program Totals | Board Priority Ranking
| JK | RS | DC | GD | JB | SE | MH | RC | CI | AA
Technical Assistance | 8 | 40 | 1 | 60 | 51 | 60 | 60 | 85 | 5 | 5 | 375 | H
Education and Outreach | 24 | 20 | 207 | 20 | 39 | 30 | 30 | 30 | 0 | 65 | 465 | H
District Operations | 185 | 120 | 25 | 40 | 42 | 25 | 35 | 30 | 2 | 150 | 654 | H
NRCS Program Assistance | 2 | 8 | 0 | 25 | 60 | 22 | 20 | 45 | 0 | 3 | 185 | H
Landowner Assistance Program | 3 | 30 | 1 | 60 | 25 | 10 | 15 | 30 | 0 | 3 | 177 | H
OWEB Grants | 3 | 10 | 1 | 20 | 15 | 20 | 10 | 15 | 0 | 3 | 97 | M
Water Quality Monitoring | 4 | 2 | 0 | 10 | 0 | 28 | 20 | 0 | 23 | 2 | 89 | M
Knotweed Program | 3 | 2 | 0 | 0 | 1 | 0 | 15 | 0 | 10 | 2 | 33 | L
Flow Monitoring | 3 | 3 | 0 | 0 | 2 | 40 | 30 | 0 | 35 | 2 | 115 | L
Total Days | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 75 | 235
Full Time Equivalent (FTE) | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.31915 | 1
Tracking
Mid-Year
End-of-Year
Volunteer Days Allocated
|  |  | Elected Directors |  |  |  |  | Associate Directors
Board of Directors | Staff Work Days Allocated DC: 80; Staff Work Days Allocated RC: 60
* See page 12 for descriptions
Staff: JK=Jane Keppinger, RS=Robin Straughan, DC=Diane Cheyne, GD=Glenn Dolphin, JB=Jeremy Baker, SE=Scott Eden, MH=Marcie Hagen, RC=Resource Conservationist, CI=Conservation Intern, AA=Administrative Assistant

## Tech Assistance
Objective 1: | Provide Conservation Planning, Technical, and Financial Assistance to Property Owners and Operators
Primary Goal: | Provide assistance to help landowners/operators get conservation on the ground
Target: | Respond to new landowner requests within one week so that the District is known to be prompt and efficient
Action Items |  | Work Days Allocated
|  | JK | RS | DC | GD | JB | SE | MH | RC | CI | AA
|  | 8 | 40 | 1 | 60 | 51 | 60 | 60 | 85 | 5 | 5 | Key Tasks Completed
Administrative | Develop/oversee budget | bar: Work Days Allocated JK to Work Days Allocated RS; Work Days Allocated JB
Provide support to technical staff/projects | bar: Work Days Allocated JK to Work Days Allocated RS; Work Days Allocated GD to Work Days Allocated JB; Work Days Allocated RC to Work Days Allocated AA
Maintain landowner, technical files | bar: Work Days Allocated RS; Work Days Allocated GD to Work Days Allocated JB; Work Days Allocated RC to Work Days Allocated CI
General assistance | Assist walk-ins/phone/e-mail technical requests | bar: Work Days Allocated RS to Work Days Allocated RC; Work Days Allocated AA
Provide partners/councils with technical assistance | bar: Work Days Allocated RS; Work Days Allocated GD to Work Days Allocated RC
Inform landowners about SB 1010 | bar: Work Days Allocated RS to Work Days Allocated RC
Assist with maintenance of weather stations | bar: Work Days Allocated JB to Work Days Allocated RC
Planning | Conduct site vists, field inventory, assess concerns | bar: Work Days Allocated RS; Work Days Allocated GD to Work Days Allocated CI
Develop conservation plans and maps | bar: Work Days Allocated RS; Work Days Allocated GD to Work Days Allocated RC
Develop ODA animal waste management plans | bar: Work Days Allocated GD; Work Days Allocated SE to Work Days Allocated RC
Assist with non-OWEB/LAP/NRCS grants | bar: Work Days Allocated RS; Work Days Allocated GD to Work Days Allocated RC
Implementation | Assist with project implementation | bar: Work Days Allocated RS; Work Days Allocated GD to Work Days Allocated RC
Report project completion | bar: Work Days Allocated RS; Work Days Allocated GD to Work Days Allocated RC
Coordinate volunteers | bar: Work Days Allocated RS to Work Days Allocated RC; Work Days Allocated AA
Training | Attend technical workshops/classes | bar: Work Days Allocated JK to Work Days Allocated RS; Work Days Allocated GD to Work Days Allocated AA
Hold/attend monthly technical staff meetings | bar: Work Days Allocated JK to Work Days Allocated RS; Work Days Allocated GD to Work Days Allocated CI
LMA Tasks | Create scope of work for LMA/TA funding from ODA | bar: Work Days Allocated RS; Work Days Allocated GD
Coordinate Local Advisory Committee (biennially)
Perform tracking and reporting for SB 1010 | bar: Work Days Allocated JK to Work Days Allocated RS; Work Days Allocated GD to Work Days Allocated RC
Tracking
Mid-Year (days spent on tasks)
End-of-Year (days spent on tasks)
% of target met

## Education
Objective 2: | Deliver Conservation Education Materials and Workshops
Goal: | Conduct education and outreach activities to encourage conservation and understanding of natural resources
Target: | Gain 10% more names and addresses for the District mailing list
Target: | 75% of classrooms receiving poster contest materials will participate in the poster contest
Target: | 50% of Oregon Envirothon will be funded through sources other than Marion SWCD
Target: | 25% of workshop/tour participants will implement one conservation practice
Action Items |  | Work Days Allocated
|  | JK | RS | DC | GD | JB | SE | MH | RC | CI | AA
|  | 24 | 20 | 207 | 20 | 39 | 30 | 30 | 30 | 0 | 65 | Key Tasks Completed
Administrative | Develop/oversee budget | bar: Work Days Allocated JK; Work Days Allocated DC
Coordinate scholarship with OSAC | bar: Work Days Allocated JK; Work Days Allocated DC
Program development, oversight, administration | bar: Work Days Allocated JK; Work Days Allocated DC; Work Days Allocated JB to Work Days Allocated MH
Educational Capacity | Network with partners/councils | bar: Work Days Allocated JK to Work Days Allocated RC; Work Days Allocated AA
Expand curriculum sources | bar: Work Days Allocated DC; Work Days Allocated SE
Apply for grants to fund outreach programs/events | bar: Work Days Allocated DC; Work Days Allocated JB to Work Days Allocated SE
Coordinate volunteers for events | bar: Work Days Allocated DC to Work Days Allocated RC; Work Days Allocated AA
Events/ Activities | Coordinate/assist with Native Plant and Tree Sale | bar: Work Days Allocated JK to Work Days Allocated RC; Work Days Allocated AA
Coordinate/assist with Oregon Envirothon | bar: Work Days Allocated RS to Work Days Allocated RC; Work Days Allocated AA
Coordinate/assist with Annual Poster Contest | bar: Work Days Allocated DC; Work Days Allocated AA
Conduct outreach at events, conferences, and fairs | bar: Work Days Allocated JK to Work Days Allocated RC; Work Days Allocated AA
Develop/perform presentations | bar: Work Days Allocated RS to Work Days Allocated RC
Organize/assist with workshops | bar: Work Days Allocated JK to Work Days Allocated RC; Work Days Allocated AA
Conduct educational tours | bar: Work Days Allocated RS to Work Days Allocated GD
Outreach | Create/distribute outreach materials | bar: Work Days Allocated JK to Work Days Allocated RC; Work Days Allocated AA
Create/update displays | bar: Work Days Allocated DC to Work Days Allocated RC; Work Days Allocated AA
Compose/assist with outreach articles | bar: Work Days Allocated JK to Work Days Allocated RC
Compile/distribute quarterly newsletter | bar: Work Days Allocated DC; Work Days Allocated AA
Order/dispense promotional items | bar: Work Days Allocated DC
Keep website up-to-date and track visits | bar: Work Days Allocated RS to Work Days Allocated DC
Write/submit press releases | bar: Work Days Allocated JK; Work Days Allocated DC; Work Days Allocated SE to Work Days Allocated MH
Create/publish advertisements | bar: Work Days Allocated DC; Work Days Allocated MH; Work Days Allocated AA
Tracking
Mid-Year (days spent on tasks)
End-of-Year (days spent on tasks)
% of target met

## District Ops
Objective 3: | Administer District Operations
Goal: | Effectively and efficiently operate the District
Target: | Conduct all required administrative tasks in a timely and efficient manner
Action Items |  | Work Days Allocated
|  | JK | RS | DC | GD | JB | SE | MH | RC | CI | AA
|  | 185 | 120 | 25 | 40 | 42 | 25 | 35 | 30 | 2 | 150 | Key Tasks Completed
Board assistance | Prepare for/attend monthly board/committee meetings | bar: Work Days Allocated JK to Work Days Allocated RC; Work Days Allocated AA
Prepare monthly board/committee minutes | bar: Work Days Allocated JK to Work Days Allocated RS; Work Days Allocated AA
Increase understanding of director roles/responsibilities | bar: Work Days Allocated JK to Work Days Allocated RS
Recruit/orient new board/committee members | bar: Work Days Allocated JK to Work Days Allocated RS; Work Days Allocated GD to Work Days Allocated MH
Prepare/file reports, memos, correspondence | bar: Work Days Allocated JK to Work Days Allocated AA
Customer service | Assist walk-in clients | bar: Work Days Allocated JK to Work Days Allocated RC; Work Days Allocated AA
Receive/direct phone calls and e-mails | bar: Work Days Allocated JK to Work Days Allocated AA
Provide watershed councils with administrative support | bar: Work Days Allocated JK; Work Days Allocated AA
District goals/ requirements | Annually update business plan, work plan | bar: Work Days Allocated JK to Work Days Allocated RC; Work Days Allocated AA
Create/publish/distribute Annual Report | bar: Work Days Allocated JK to Work Days Allocated RC; Work Days Allocated AA
Attend partner/council meetings | bar: Work Days Allocated JK to Work Days Allocated RS; Work Days Allocated GD to Work Days Allocated RC; Work Days Allocated AA
Assist with/attend OACD annual conference, meetings | bar: Work Days Allocated JK to Work Days Allocated GD; Work Days Allocated RC; Work Days Allocated AA
Hold/attend monthly staff meetings | bar: Work Days Allocated JK to Work Days Allocated AA
Attend administrative trainings, workshops, conferences | bar: Work Days Allocated JK to Work Days Allocated RS; Work Days Allocated AA
Hold/attend Annual Meeting | bar: Work Days Allocated JK to Work Days Allocated RC; Work Days Allocated AA
Financial management | Complete Oregon Budget Law requirements | bar: Work Days Allocated JK to Work Days Allocated RS; Work Days Allocated AA
Prepare for annual audit | bar: Work Days Allocated JK; Work Days Allocated AA
Perform monthly payroll and quarterly reports | bar: Work Days Allocated JK
Perform monthly A/R, A/P | bar: Work Days Allocated JK
Create/correlate monthly financial statements | bar: Work Days Allocated JK
Manage/develop contracts, agreements | bar: Work Days Allocated JK to Work Days Allocated RS; Work Days Allocated AA
Office management | Perform staff hiring/performance appraisals | bar: Work Days Allocated JK to Work Days Allocated RC
Maintain/update policies, job descriptions, forms | bar: Work Days Allocated JK to Work Days Allocated RS; Work Days Allocated AA
Maintain mailing lists | bar: Work Days Allocated JK to Work Days Allocated DC; Work Days Allocated AA
Maintain equipment/vehicles | bar: Work Days Allocated JK to Work Days Allocated RC
Conduct filing, database, office maintenance | bar: Work Days Allocated JK to Work Days Allocated AA
Order/purchase supplies | bar: Work Days Allocated JK to Work Days Allocated RC; Work Days Allocated AA
Complete regular tracking, reporting, requests | bar: Work Days Allocated JK to Work Days Allocated RC; Work Days Allocated AA
Assist with pursuit of permanent facility | bar: Work Days Allocated JK to Work Days Allocated RS
Tracking
Mid-Year (days spent on tasks)
End-of-Year (days spent on tasks)
% of target met

## NRCS
Objective 4: | Implement Programs that Assist Constituents with Natural Resource Concerns
Goal: | Provide assistance to help landowners get conservation on the ground
Target: | Assist NRCS with a minimum of 10 landowner projects to meet priorities set by local stakeholders
Action Items |  | Work Days Allocated
|  | JK | RS | DC | GD | JB | SE | MH | RC | CI | AA
|  | 2 | 8 | 0 | 25 | 60 | 22 | 20 | 45 | 0 | 3 | Key Tasks Completed
Administrative | Develop/track progress for Contribution Agreement | bar: Work Days Allocated JK to Work Days Allocated RS; Work Days Allocated JB; Work Days Allocated RC; Work Days Allocated AA
Develop/oversee budget | bar: Work Days Allocated JK to Work Days Allocated RS; Work Days Allocated JB; Work Days Allocated RC
Maintain landowner files | bar: Work Days Allocated RS; Work Days Allocated GD to Work Days Allocated RC; Work Days Allocated AA
Assist with program oversight
Help with project screening, ranking | bar: Work Days Allocated JB; Work Days Allocated RC
Conduct correspondence with program participants | bar: Work Days Allocated GD to Work Days Allocated RC; Work Days Allocated AA
Conduct annual stakeholder meeting | bar: Work Days Allocated JB
Planning | Conduct site vists, field inventory, assess concerns | bar: Work Days Allocated RS; Work Days Allocated GD to Work Days Allocated RC
Develop conservation plans, contracts, maps | bar: Work Days Allocated GD to Work Days Allocated RC
Develop project specifications | bar: Work Days Allocated GD to Work Days Allocated RC
Implementation | Assist with funded project implementation | bar: Work Days Allocated GD to Work Days Allocated RC
Verify/report implemented projects | bar: Work Days Allocated GD to Work Days Allocated RC
Conduct annual status reviews | bar: Work Days Allocated RS; Work Days Allocated GD to Work Days Allocated JB; Work Days Allocated RC
Training | Attend trainings/meetings | bar: Work Days Allocated GD to Work Days Allocated RC
Obtain/maintain planner certification | bar: Work Days Allocated JB to Work Days Allocated RC
Tracking
Mid-Year (days spent on tasks)
End-of-Year (days spent on tasks)
% of target met

## LAP
Objective 4: | Implement Programs that Assist Constituents with Natural Resource Concerns
Primary Goal: | Provide assistance to help landowners get conservation on the ground
Target: | Get 10 new projects implemented that help landowners meet SB1010
Action Items |  | Work Days Allocated
|  | JK | RS | DC | GD | JB | SE | MH | RC | CI | AA
|  | 3 | 30 | 1 | 60 | 25 | 10 | 15 | 30 | 0 | 3 | Key Tasks Completed
Administrative | Program development, oversight, administration | bar: Work Days Allocated JK to Work Days Allocated RS; Work Days Allocated GD to Work Days Allocated JB; Work Days Allocated AA
Develop/oversee budget | bar: Work Days Allocated JK to Work Days Allocated RS; Work Days Allocated GD
Maintain landowner files | bar: Work Days Allocated RS; Work Days Allocated GD to Work Days Allocated RC
Advertise and write press releases | bar: Work Days Allocated RS to Work Days Allocated DC; Work Days Allocated AA
Create/coordinate installation of signs | bar: Work Days Allocated RS; Work Days Allocated GD to Work Days Allocated RC; Work Days Allocated AA
Attend meetings | bar: Work Days Allocated RS; Work Days Allocated GD to Work Days Allocated RC
Review/rank applications | bar: Work Days Allocated RS; Work Days Allocated GD to Work Days Allocated RC
Recommend project funding | bar: Work Days Allocated RS; Work Days Allocated GD to Work Days Allocated RC
Conduct correspondence with program participants | bar: Work Days Allocated RS; Work Days Allocated GD to Work Days Allocated RC; Work Days Allocated AA
Review bills for reimbursement, make payment | bar: Work Days Allocated RS; Work Days Allocated GD to Work Days Allocated RC
Planning | Conduct site vists, field inventory, assess concerns | bar: Work Days Allocated RS; Work Days Allocated GD to Work Days Allocated RC
Develop conservation plans and maps | bar: Work Days Allocated RS; Work Days Allocated GD to Work Days Allocated RC
Develop project specifications | bar: Work Days Allocated RS; Work Days Allocated GD to Work Days Allocated RC
Implementation | Assist with funded project implementation | bar: Work Days Allocated RS; Work Days Allocated GD to Work Days Allocated RC
Verify/report implemented projects | bar: Work Days Allocated RS; Work Days Allocated GD to Work Days Allocated RC
Conduct annual inspections | bar: Work Days Allocated RS; Work Days Allocated GD to Work Days Allocated RC
Tracking
Mid-Year (days spent on tasks)
End-of-Year (days spent on tasks)
% of target met

## OWEB Grants
Objective 4: | Implement Programs that Assist Constituents with Natural Resource Concerns
Goal: | Provide assistance to help landowners get conservation on the ground
Target: | Provide landowners with moderate priorty projects an opportunity to submit them in March '07
Target: | Get 5 new projects implemented that improve or restore priority upland or riparian conditions
Action Items |  | Work Days Allocated
|  | JK | RS | DC | GD | JB | SE | MH | RC | CI | AA
|  | 3 | 10 | 1 | 20 | 15 | 20 | 10 | 15 | 0 | 3 | Key Tasks Completed
Administrative | Program development, oversight, administration | bar: Work Days Allocated JK; Work Days Allocated GD; Work Days Allocated SE; Work Days Allocated AA
Develop/oversee budget | bar: Work Days Allocated JK; Work Days Allocated GD; Work Days Allocated SE
Attend grant team meetings, rank grants | bar: Work Days Allocated GD; Work Days Allocated SE
Maintain landowner files | bar: Work Days Allocated RS; Work Days Allocated GD to Work Days Allocated RC; Work Days Allocated AA
Advertise and write press releases | bar: Work Days Allocated DC; Work Days Allocated SE; Work Days Allocated AA
Conduct correspondence with program participants | bar: Work Days Allocated RS; Work Days Allocated GD to Work Days Allocated RC; Work Days Allocated AA
Review and submit bills for reimbursement | bar: Work Days Allocated RS; Work Days Allocated GD to Work Days Allocated RC
Planning | Conduct site vists, field inventory, assess concerns | bar: Work Days Allocated RS; Work Days Allocated GD to Work Days Allocated RC
Develop conservation plans and maps | bar: Work Days Allocated RS; Work Days Allocated GD to Work Days Allocated RC
Complete/review grant applications | bar: Work Days Allocated RS; Work Days Allocated GD to Work Days Allocated RC
Develop project specifications | bar: Work Days Allocated RS; Work Days Allocated GD to Work Days Allocated RC
Implementation | Assist with funded project implementation | bar: Work Days Allocated RS; Work Days Allocated GD to Work Days Allocated RC
Verify/report implemented projects | bar: Work Days Allocated RS; Work Days Allocated GD to Work Days Allocated RC
Help coordinate volunteers | bar: Work Days Allocated RS to Work Days Allocated RC; Work Days Allocated AA
Assist with 2-year project report | bar: Work Days Allocated RS; Work Days Allocated GD to Work Days Allocated RC
Tracking
Mid-Year (days spent on tasks)
End-of-Year (days spent on tasks)
% of target met

## WQ
Objective 4: | Implement Programs that Assist Constituents with Natural Resource Concerns
Goal: | Collect data to monitor implementation of SB 1010 and use to help improve water quality conditions
Target: | Find 5 new volunteers to assist with monitoring efforts
Target: | Assist with 5 local school projects for water quality
Action Items |  | Work Days Allocated
|  | JK | RS | DC | GD | JB | SE | MH | RC | CI | AA
|  | 4 | 2 | 0 | 10 | 0 | 28 | 20 | 0 | 23 | 2 | Key Tasks Completed
Administrative | Program development, oversight, administration | bar: Work Days Allocated JK to Work Days Allocated RS; Work Days Allocated SE to Work Days Allocated MH; Work Days Allocated AA
Develop/oversee budget | bar: Work Days Allocated JK; Work Days Allocated SE
Attend meetings | bar: Work Days Allocated GD; Work Days Allocated SE to Work Days Allocated MH; Work Days Allocated CI
Purchase equipment and supplies | bar: Work Days Allocated SE to Work Days Allocated MH
Analysis | Interpret, analyze data | bar: Work Days Allocated SE to Work Days Allocated MH; Work Days Allocated CI
Publish/utilize data; share with agencies, public | bar: Work Days Allocated SE to Work Days Allocated MH
Field | Calibrate/maintain equipment, summer loggers | bar: Work Days Allocated GD; Work Days Allocated SE to Work Days Allocated MH; Work Days Allocated CI
Install summer loggers | bar: Work Days Allocated GD; Work Days Allocated SE to Work Days Allocated MH; Work Days Allocated CI
Conduct water quality sampling/testing | bar: Work Days Allocated GD; Work Days Allocated SE to Work Days Allocated MH; Work Days Allocated CI
Coordinate/train staff/volunteers | bar: Work Days Allocated GD; Work Days Allocated SE to Work Days Allocated MH
Conduct trials/experiments | bar: Work Days Allocated GD; Work Days Allocated SE to Work Days Allocated MH
Other Tasks for 319 Grant | Conduct outreach, landowner education | bar: Work Days Allocated GD; Work Days Allocated SE to Work Days Allocated MH
Coordinate/partner with DEQ | bar: Work Days Allocated JK; Work Days Allocated GD; Work Days Allocated SE
Assist with implementation of BMPs | bar: Work Days Allocated GD; Work Days Allocated SE to Work Days Allocated MH
Conduct grant reporting, track progress | bar: Work Days Allocated JK; Work Days Allocated GD; Work Days Allocated SE
Tracking
Mid-Year (days spent on tasks)
End-of-Year (days spent on tasks)
% of target met

## Knotweed
Objective 4: | Implement Programs that Assist Constituents with Natural Resource Concerns
Goal: | Assist landowners in targeted watersheds with identification and eradication of knotweed
Target: | Eradicate all known knotweed sites within the program
Action Items |  | Work Days Allocated
|  | JK | RS | DC | GD | JB | SE | MH | RC | CI | AA
|  | 3 | 2 | 0 | 0 | 1 | 0 | 15 | 0 | 10 | 2 | Key Tasks Completed
Administrative | Program development, oversight, administration | bar: Work Days Allocated JK to Work Days Allocated RS; Work Days Allocated MH; Work Days Allocated AA
Track grant activities/budget | bar: Work Days Allocated JK; Work Days Allocated MH
Attend weed partnership meetings | bar: Work Days Allocated MH
Maintain landowner, technical files | bar: Work Days Allocated MH; Work Days Allocated CI
Conduct correspondence with program participants | bar: Work Days Allocated MH; Work Days Allocated CI to Work Days Allocated AA
Outreach | Obtain/create target mailing list | bar: Work Days Allocated MH
Develop/mail outreach letters | bar: Work Days Allocated MH
Field | Train staff on surveying | bar: Work Days Allocated MH
Conduct field surveying | bar: Work Days Allocated MH; Work Days Allocated CI
Develop site maps | bar: Work Days Allocated MH; Work Days Allocated CI
Treatment | Contract with pesticide applicator | bar: Work Days Allocated MH
Assist with treatment | bar: Work Days Allocated JB; Work Days Allocated CI
Verify treatment effectiveness | bar: Work Days Allocated MH; Work Days Allocated CI
Tracking
Mid-Year (days spent on tasks)
End-of-Year (days spent on tasks)
% of target met

## Flow
Objective 4: | Implement Programs that Assist Constituents with Natural Resource Concerns
Goal: | Provide consituents and partners with stream flow and level information
Target: | Collect 40 representative stream velocity measurements
Target: | Install new real-time monitoring equipment at 5 locations
Action Items |  | Work Days Allocated
|  | JK | RS | DC | GD | JB | SE | MH | RC | CI | AA
|  | 3 | 3 | 0 | 0 | 2 | 40 | 30 | 0 | 35 | 2 | Key Tasks Completed
Administrative | Program development, oversight, administration | bar: Work Days Allocated JK to Work Days Allocated RS; Work Days Allocated SE to Work Days Allocated MH; Work Days Allocated AA
Develop/oversee budget | bar: Work Days Allocated JK; Work Days Allocated SE
Purchase equipment and supplies | bar: Work Days Allocated SE
Analysis | Interpret, analyze data | bar: Work Days Allocated SE to Work Days Allocated MH; Work Days Allocated CI
Publish/utilize data | bar: Work Days Allocated SE to Work Days Allocated MH
Provide web-based interface for data | bar: Work Days Allocated SE
Field | Calibrate/maintain equipment | bar: Work Days Allocated SE to Work Days Allocated MH; Work Days Allocated CI
Conduct monthly flow monitoring | bar: Work Days Allocated SE to Work Days Allocated MH; Work Days Allocated CI
Coordinate/train staff/volunteers | bar: Work Days Allocated SE to Work Days Allocated MH
Install new equipment | bar: Work Days Allocated JB to Work Days Allocated MH; Work Days Allocated CI
Tracking
Mid-Year (days spent on tasks)
End-of-Year (days spent on tasks)
% of target met

## Board
Action Items |  | Volunteer Days Allocated
|  | Elected Directors | Associate Directors
|  | 80 | 60
Board/Committee meetings | Attend board/committee meetings | X | X
| Approve meeting minutes, financial reports | X
| Approve conservation plans | X
| Approve policies, contracts, job descriptions | X
| Approve annual work plan, budget, and audit | X
| Update/approve business plan | X | X
| Approve staff hiring/performance appraisals | X
| Attend Annual Meeting | X | X
Director responsibility | Review board/committee packet materials | X | X
| Meet with/call staff as necessary | X | X
| Assist with personnel issues as necessary | X | X
| Provide operational oversight | X | X
| Understand director roles and responsibilities | X | X
| Attend trainings, workshops, conferences | X | X
| Attend partner/council meetings | X | X
| Attend OACD/NACD annual conferences | X | X
District assistance | Recruit new directors and associate directors | X | X
| Attend/assist with events, activities, programs | X | X
| Promote the District among peers, constituents | X | X
| Give direction/assistance with pursuing permanent District facility | X | X

## Descriptions
Focus Area | Program Description/Goals | Lead
District Operations | · The goal is to provide effective operational planning and oversight of the district | JK, RS
· Key components are budgetary preparation and control, purchases, payments, audits, and reports, safety, risk management, personnel, vehicle and equipment maintenance, facilities management, and board development
Education/Outreach | · The goal is to deliver soil and water conservation related materials to the youth and adults of Marion County | DC
· Products include displays, ads, press releases, brochures, promotional items, website, etc.
· Events include Native Plant & Tree Sale (JB & DC co-lead), Envirothon, Poster Contest, workshops, tours, presentations to groups
Flow Monitoring | · The goal is to gather and analyze data to assess local stream flow conditions and provide information on water quantity | SE
· Six permanent stations are installed on creeks where staff gage height is recorded; actual water flows are measured during the low-flow season
· The program will transition to real-time loggers once enough field data is collected to develop rating curves
Knotweed Program | · The goal is eradication of knotweed in the Abiqua Creek, Croisan Creek, Brush Creek, and Drift Creek watersheds where known sites have been identified and treated | MH
Landowner Assistance Program (LAP) | · This is our own grant program for small acreage landowners to implement conservation practices, especially related to agricultural water quality and livestock management | GD & RS
· Projects that have high demonstration value are encouraged
NRCS Program Assistance | · The District provides help with ranking, planning, and contracting, and implementation of NRCS projects, especially with EQIP, CREP, and CSP funds | JB
· These cost-share programs help larger acreage agricultural landowners implement conservation priority practices set by local stakeholders
Oregon Watershed Enhancement Board (OWEB) Grants | · These grant programs are for any landowners addressing water quality issues, especially streamside plantings, fencing livestock from streams, fish passage, etc. | GD & SE
· Staff serve on team representing Linn & Marion counties for the small grant program
Technical Assistance | · The goal is to provide planning and advice to landowners and others requesting help with natural resource-related projects | RS
· Includes guidance for helping landowners meet the agricultural water quality plan goals
· Two weather stations are maintained to provide data to farmers for making decisions about irrigation, chemical applications, etc. (JB leads)
Water Quality Monitoring | · This is a long-term program to conduct water quality sampling and testing in the Pudding River Watershed, which addresses agricultural water quality plan | SE
· The goals include determining baseline conditions, identifying trends, and conducting outreach to help improve landowner awareness & water conditions
· Includes Section 319 EPA/DEQ grant which funds the Pudding River Pesticide Stewardship Network (GD & SE co-lead)